## Planned cost
Activity ID | WBS | Activity Name | Subcontractor | Budget | Date | Planned Cost | Country | State
A1050 | Structural Works | Civil Works | Khonamon | 2500 | 2022-02-01 | 2500 | Spain | Madrid
A1060 | Structural Works | Waterproofing/Anti-Termite | Khonamon | 800 | 2022-02-01 | 666.67 | France | Paris
A1060 | Structural Works | Waterproofing/Anti-Termite | Khonamon | 800 | 2022-02-08 | 133.33 | France | Paris
A1070 | Structural Works | Lean Concrete | Khonamon | 2200 | 2022-02-08 | 2200 | France | Paris
A1080 | Structural Works | Foundation (Rebar, Formwork, Concrete) | Khonamon | 12300 | 2022-02-08 | 5271.43 | Spain | Madrid
A1080 | Structural Works | Foundation (Rebar, Formwork, Concrete) | Khonamon | 12300 | 2022-02-15 | 7028.57 | Spain | Madrid
A1090 | Structural Works | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | Khonamon | 14500 | 2022-02-15 | 725 | Spain | Madrid
A1090 | Structural Works | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | Khonamon | 14500 | 2022-02-22 | 9425 | Spain | Madrid
A1090 | Structural Works | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | Khonamon | 14500 | 2022-03-01 | 4350 | Spain | Madrid
A1100 | Structural Works | Slabs, beams, staircases concrete 1 Floor | Khonamon | 15500 | 2022-03-08 | 11071.43 | Spain | Madrid
A1100 | Structural Works | Slabs, beams, staircases concrete 1 Floor | Khonamon | 15500 | 2022-03-15 | 4428.57 | Spain | Madrid
A1110 | Structural Works | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | Khonamon | 16500 | 2022-03-15 | 2475 | Spain | Madrid
A1110 | Structural Works | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | Khonamon | 16500 | 2022-03-22 | 10725 | Spain | Madrid
A1110 | Structural Works | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | Khonamon | 16500 | 2022-03-29 | 3300 | Spain | Madrid
A1120 | Structural Works | Slabs, beams 2 Floor | Khonamon | 17500 | 2022-04-05 | 8263.89 | Spain | Madrid
A1120 | Structural Works | Slabs, beams 2 Floor | Khonamon | 17500 | 2022-04-12 | 9236.11 | Spain | Madrid
A1130 | Masonry Works | Masonry Works | Khonamon | 5500 | 2022-03-22 | 1222.22 | France | Lyon
A1130 | Masonry Works | Masonry Works | Khonamon | 5500 | 2022-03-29 | 1451.39 | France | Lyon
A1130 | Masonry Works | Masonry Works | Khonamon | 5500 | 2022-04-05 | 1986.11 | France | Lyon
A1130 | Masonry Works | Masonry Works | Khonamon | 5500 | 2022-04-12 | 840.28 | France | Lyon
A1140 | Roof | Roof Steel Structure | Khonamon | 4500 | 2022-04-26 | 3696.43 | #N/A | #N/A
A1140 | Roof | Roof Steel Structure | Khonamon | 4500 | 2022-05-03 | 803.57 | #N/A | #N/A
A1150 | Roof | Middle Frames Installation | Khonamon | 950 | 2022-05-03 | 950 | #N/A | #N/A
A1160 | Roof | Installation of Metal Sheets | Khonamon | 4700 | 2022-05-03 | 4700 | #N/A | #N/A
A1170 | Roof | Waterproofing | Khonamon | 1400 | 2022-05-03 | 875 | #N/A | #N/A
A1170 | Roof | Waterproofing | Khonamon | 1400 | 2022-05-10 | 525 | #N/A | #N/A
A1180 | Roof | Clay Tiles | Khonamon | 2800 | 2022-05-10 | 2800 | #N/A | #N/A
A1190 | Terraces | Terrace Heat Insulation | Pemax | 217.49 | 2022-03-29 | 190.3 | France | Lyon
A1190 | Terraces | Terrace Heat Insulation | Pemax | 217.49 | 2022-04-05 | 27.19 | France | Lyon
A1200 | Terraces | Terraces Sloped Screed | Pemax | 434.96 | 2022-04-05 | 434.96 | France | Lyon
A1210 | Terraces | Terraces Waterproofing | Pemax | 855.43 | 2022-04-05 | 855.43 | Spain | Barcelona
A1220 | Terraces | Finishing | Pemax | 2174.82 | 2022-05-10 | 2066.08 | #N/A | #N/A
A1220 | Terraces | Finishing | Pemax | 2174.82 | 2022-05-17 | 108.74 | #N/A | #N/A
A1230 | Façade | Sub Frame for Windows | Pemax | 3131.75 | 2022-04-26 | 2125.12 | #N/A | #N/A
A1230 | Façade | Sub Frame for Windows | Pemax | 3131.75 | 2022-05-03 | 1006.63 | #N/A | #N/A
A1240 | Façade | Windows & Doors | Pemax | 11599.06 | 2022-05-03 | 3521.14 | #N/A | #N/A
A1240 | Façade | Windows & Doors | Pemax | 11599.06 | 2022-05-10 | 5385.28 | #N/A | #N/A
A1240 | Façade | Windows & Doors | Pemax | 11599.06 | 2022-05-17 | 2692.64 | #N/A | #N/A
A1250 | Façade | Curtain Wall | Pemax | 11599.06 | 2022-05-03 | 4929.6 | #N/A | #N/A
A1250 | Façade | Curtain Wall | Pemax | 11599.06 | 2022-05-10 | 6669.46 | #N/A | #N/A
A1260 | Façade | Sliding Doors | Pemax | 11599.06 | 2022-05-03 | 3521.14 | #N/A | #N/A
A1260 | Façade | Sliding Doors | Pemax | 11599.06 | 2022-05-10 | 5385.28 | #N/A | #N/A
A1260 | Façade | Sliding Doors | Pemax | 11599.06 | 2022-05-17 | 2692.64 | #N/A | #N/A
A1270 | Façade | EPS Fixing | Pemax | 1667.37 | 2022-04-26 | 1131.43 | #N/A | #N/A
A1270 | Façade | EPS Fixing | Pemax | 1667.37 | 2022-05-03 | 535.94 | #N/A | #N/A
A1280 | Façade | Plaster for Walls | Pemax | 2218.32 | 2022-05-03 | 1571.31 | #N/A | #N/A
A1280 | Façade | Plaster for Walls | Pemax | 2218.32 | 2022-05-10 | 647.01 | #N/A | #N/A
A1290 | Façade | Stone | Pemax | 7524.89 | 2022-05-10 | 2553.09 | #N/A | #N/A
A1290 | Façade | Stone | Pemax | 7524.89 | 2022-05-17 | 3493.7 | #N/A | #N/A
A1290 | Façade | Stone | Pemax | 7524.89 | 2022-05-24 | 1478.1 | #N/A | #N/A
A1300 | Façade | Decorative Plaster | Pemax | 2551.79 | 2022-05-24 | 2392.3 | #N/A | #N/A
A1300 | Façade | Decorative Plaster | Pemax | 2551.79 | 2022-05-31 | 159.49 | #N/A | #N/A
A1310 | Façade | Shutters&Louvers | Pemax | 130.49 | 2022-05-17 | 60.58 | #N/A | #N/A
A1310 | Façade | Shutters&Louvers | Pemax | 130.49 | 2022-05-24 | 69.91 | #N/A | #N/A
A1320 | Façade | Exterior Balustrades | Pemax | 8684.8 | 2022-06-28 | 7754.29 | #N/A | #N/A
A1320 | Façade | Exterior Balustrades | Pemax | 8684.8 | 2022-07-05 | 930.51 | #N/A | #N/A
A1330 | Fit-out | Framing for Gypsum Walls | Pemax | 7466.9 | 2022-04-26 | 2533.41 | #N/A | #N/A
A1330 | Fit-out | Framing for Gypsum Walls | Pemax | 7466.9 | 2022-05-03 | 3466.78 | #N/A | #N/A
A1330 | Fit-out | Framing for Gypsum Walls | Pemax | 7466.9 | 2022-05-10 | 1466.71 | #N/A | #N/A
A1340 | Fit-out | Gypsum Board Lining for Walls | Pemax | 5973.51 | 2022-05-17 | 186.67 | #N/A | #N/A
A1340 | Fit-out | Gypsum Board Lining for Walls | Pemax | 5973.51 | 2022-05-24 | 4853.48 | #N/A | #N/A
A1340 | Fit-out | Gypsum Board Lining for Walls | Pemax | 5973.51 | 2022-05-31 | 933.36 | #N/A | #N/A
A1350 | Fit-out | Framing of Suspended Ceilings | Pemax | 1826.85 | 2022-05-31 | 1370.14 | #N/A | #N/A
A1350 | Fit-out | Framing of Suspended Ceilings | Pemax | 1826.85 | 2022-06-07 | 456.71 | #N/A | #N/A
A1360 | Fit-out | Gypsum Board Lining for Ceiling | Pemax | 1826.85 | 2022-06-14 | 742.16 | #N/A | #N/A
A1360 | Fit-out | Gypsum Board Lining for Ceiling | Pemax | 1826.85 | 2022-06-21 | 1084.69 | #N/A | #N/A
A1370 | Fit-out | Heat Insulation for Interiors | Pemax | 637.95 | 2022-05-31 | 637.95 | #N/A | #N/A
A1380 | Fit-out | Screed for Interiors | Pemax | 1783.36 | 2022-05-31 | 1783.36 | #N/A | #N/A
A1390 | Fit-out | Waterproofing for Wet Areas | Pemax | 855.43 | 2022-05-31 | 71.29 | #N/A | #N/A
A1390 | Fit-out | Waterproofing for Wet Areas | Pemax | 855.43 | 2022-06-07 | 784.14 | #N/A | #N/A
A1400 | Fit-out | Interior Steel Installation | Pemax | 7959.86 | 2022-04-26 | 7959.86 | #N/A | #N/A
A1410 | Finishing | Stone Wall Cladding | Pemax | 17529.08 | 2022-06-07 | 6573.41 | #N/A | #N/A
A1410 | Finishing | Stone Wall Cladding | Pemax | 17529.08 | 2022-06-14 | 10955.67 | #N/A | #N/A
A1420 | Finishing | Timber Wall Covering | Pemax | 5727.05 | 2022-06-14 | 143.18 | #N/A | #N/A
A1420 | Finishing | Timber Wall Covering | Pemax | 5727.05 | 2022-06-21 | 3722.58 | #N/A | #N/A
A1420 | Finishing | Timber Wall Covering | Pemax | 5727.05 | 2022-06-28 | 1861.29 | #N/A | #N/A
A1430 | Finishing | Paint for Wall | Pemax | 869.93 | 2022-06-28 | 706.82 | #N/A | #N/A
A1430 | Finishing | Paint for Wall | Pemax | 869.93 | 2022-07-05 | 163.11 | #N/A | #N/A
A1440 | Finishing | Wall Covering & Upholstery | Pemax | 1159.91 | 2022-07-05 | 1159.91 | #N/A | #N/A
A1450 | Finishing | Paint for Ceiling | Pemax | 1304.89 | 2022-06-28 | 1060.22 | #N/A | #N/A
A1450 | Finishing | Paint for Ceiling | Pemax | 1304.89 | 2022-07-05 | 244.67 | #N/A | #N/A
A1460 | Finishing | Stone Flooring | Pemax | 19906.89 | 2022-06-14 | 710.96 | #N/A | #N/A
A1460 | Finishing | Stone Flooring | Pemax | 19906.89 | 2022-06-21 | 18484.97 | #N/A | #N/A
A1460 | Finishing | Stone Flooring | Pemax | 19906.89 | 2022-06-28 | 710.96 | #N/A | #N/A
A1470 | Finishing | Parquet Flooring | Pemax | 536.46 | 2022-06-28 | 478.98 | #N/A | #N/A
A1470 | Finishing | Parquet Flooring | Pemax | 536.46 | 2022-07-05 | 57.48 | #N/A | #N/A
A1480 | Finishing | Stair Cladding | Pemax | 1200 | 2022-04-26 | 660 | #N/A | #N/A
A1480 | Finishing | Stair Cladding | Pemax | 1200 | 2022-05-03 | 540 | #N/A | #N/A
A1490 | Finishing | Internal Doors Installations | Pemax | 3653.7 | 2022-07-05 | 3001.25 | #N/A | #N/A
A1490 | Finishing | Internal Doors Installations | Pemax | 3653.7 | 2022-07-12 | 652.45 | #N/A | #N/A
A1500 | Finishing | Kitchen | Pemax | 724.95 | 2022-06-21 | 543.71 | #N/A | #N/A
A1500 | Finishing | Kitchen | Pemax | 724.95 | 2022-06-28 | 181.24 | #N/A | #N/A
A1510 | Finishing | Sanitary Installations | Pemax | 1391.89 | 2022-06-28 | 1391.89 | #N/A | #N/A
A1520 | Finishing | Joinery Installations | Pemax | 9134.26 | 2022-07-05 | 9134.26 | #N/A | #N/A
A1530 | Finishing | FF&E | Pemax | 1449.88 | 2022-07-05 | 362.47 | #N/A | #N/A
A1530 | Finishing | FF&E | Pemax | 1449.88 | 2022-07-12 | 1087.41 | #N/A | #N/A
A1540 | Finishing | Interior Balustrade | Pemax | 2609.79 | 2022-05-03 | 2218.32 | #N/A | #N/A
A1540 | Finishing | Interior Balustrade | Pemax | 2609.79 | 2022-05-10 | 391.47 | #N/A | #N/A
A1550 | MEP | Initial Piping Works Below Ground Level | Pemax | 4871.6 | 2022-02-08 | 2087.83 | Spain | Barcelona
A1550 | MEP | Initial Piping Works Below Ground Level | Pemax | 4871.6 | 2022-02-15 | 2783.77 | Spain | Barcelona
A1560 | MEP | Steel Pipes & Steel Works | Pemax | 10439.15 | 2022-02-08 | 2087.83 | Spain | Barcelona
A1560 | MEP | Steel Pipes & Steel Works | Pemax | 10439.15 | 2022-02-15 | 4523.63 | Spain | Barcelona
A1560 | MEP | Steel Pipes & Steel Works | Pemax | 10439.15 | 2022-02-22 | 3827.69 | Spain | Barcelona
A1570 | MEP | Internal Plumbing | Pemax | 6959.44 | 2022-05-10 | 2609.79 | #N/A | #N/A
A1570 | MEP | Internal Plumbing | Pemax | 6959.44 | 2022-05-17 | 4349.65 | #N/A | #N/A
A1580 | MEP | Ductwork & Dampers | Pemax | 10439.15 | 2022-05-10 | 2609.79 | #N/A | #N/A
A1580 | MEP | Ductwork & Dampers | Pemax | 10439.15 | 2022-05-17 | 4523.63 | #N/A | #N/A
A1580 | MEP | Ductwork & Dampers | Pemax | 10439.15 | 2022-05-24 | 3305.73 | #N/A | #N/A
A1590 | MEP | Cable Trays | Pemax | 2029.84 | 2022-05-24 | 761.19 | #N/A | #N/A
A1590 | MEP | Cable Trays | Pemax | 2029.84 | 2022-05-31 | 1268.65 | #N/A | #N/A
A1600 | MEP | Conduits | Pemax | 7104.42 | 2022-05-31 | 5328.31 | #N/A | #N/A
A1600 | MEP | Conduits | Pemax | 7104.42 | 2022-06-07 | 1776.11 | #N/A | #N/A
A1610 | MEP | Earthing & Lightning Protection | Pemax | 1014.92 | 2022-05-10 | 1014.92 | #N/A | #N/A
A1620 | MEP | Cables | Pemax | 7104.42 | 2022-06-07 | 4820.86 | #N/A | #N/A
A1620 | MEP | Cables | Pemax | 7104.42 | 2022-06-14 | 2283.56 | #N/A | #N/A
A1630 | MEP | Fan coil & Silencers & Flexible Ducts | Pemax | 3479.72 | 2022-05-24 | 1217.9 | #N/A | #N/A
A1630 | MEP | Fan coil & Silencers & Flexible Ducts | Pemax | 3479.72 | 2022-05-31 | 2261.82 | #N/A | #N/A
A1640 | MEP | Strainers & Grills | Pemax | 4871.61 | 2022-05-31 | 2261.82 | #N/A | #N/A
A1640 | MEP | Strainers & Grills | Pemax | 4871.61 | 2022-06-07 | 2609.79 | #N/A | #N/A
A1650 | MEP | Insulation | Pemax | 4871.61 | 2022-04-05 | 2261.82 | #N/A | #N/A
A1650 | MEP | Insulation | Pemax | 4871.61 | 2022-04-12 | 2609.79 | #N/A | #N/A
A1660 | MEP | Underfloor Heating System | Pemax | 4871.62 | 2022-05-31 | 173.99 | #N/A | #N/A
A1660 | MEP | Underfloor Heating System | Pemax | 4871.62 | 2022-06-07 | 4523.64 | #N/A | #N/A
A1660 | MEP | Underfloor Heating System | Pemax | 4871.62 | 2022-06-14 | 173.99 | #N/A | #N/A
A1670 | MEP | Sprinkler | Pemax | 2100 | 2022-06-14 | 2100 | #N/A | #N/A
A1680 | MEP | Embedded Lightning Fixtures | Pemax | 3044.75 | 2022-05-31 | 3044.75 | #N/A | #N/A
A1690 | MEP | Fire Hose Cabinets | Pemax | 1391.89 | 2022-06-28 | 1391.89 | #N/A | #N/A
A1700 | MEP | Slot Diffusers | Pemax | 2783.77 | 2022-07-05 | 2783.77 | #N/A | #N/A
A1710 | MEP | Switches & Sockets & Outlets | Pemax | 5074.59 | 2022-07-12 | 5074.59 | #N/A | #N/A
A1720 | MEP | ELV Equipment Installation | Pemax | 5074.59 | 2022-07-12 | 253.73 | #N/A | #N/A
A1720 | MEP | ELV Equipment Installation | Pemax | 5074.59 | 2022-07-19 | 4820.86 | #N/A | #N/A
A1730 | MEP | Roof Lighting Protection | Pemax | 3044.75 | 2022-05-24 | 3044.75 | #N/A | #N/A
A1740 | MEP | Cabinets&Panels | Pemax | 7104.42 | 2022-07-05 | 761.19 | #N/A | #N/A
A1740 | MEP | Cabinets&Panels | Pemax | 7104.42 | 2022-07-12 | 6343.23 | #N/A | #N/A

## Actual cost
Activity ID | Activity Name | Total | Date | Actual Cost | Country | State
A1050 | Civil Works | 2500 | 2022-02-01 | 2500 | Spain | Madrid
A1060 | Waterproofing/Anti-Termite | 800 | 2022-02-01 | 666.67 | France | Paris
A1060 | Waterproofing/Anti-Termite | 800 | 2022-02-08 | 133.33 | Spain | Barcelona
A1070 | Lean Concrete | 2200 | 2022-02-08 | 2200 | France | Paris
A1080 | Foundation (Rebar, Formwork, Concrete) | 12000 | 2022-02-08 | 1770.49 | Spain | Madrid
A1080 | Foundation (Rebar, Formwork, Concrete) | 12000 | 2022-02-15 | 10229.51 | France | Paris
A1090 | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | 13500 | 2022-02-22 | 7256.25 | Spain | Madrid
A1090 | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | 13500 | 2022-03-01 | 6243.75 | France | Paris
A1100 | Slabs, beams, staircases concrete 1 Floor | 16000 | 2022-03-08 | 11428.57 | Spain | Madrid
A1100 | Slabs, beams, staircases concrete 1 Floor | 16000 | 2022-03-15 | 4571.43 | France | Lyon
A1110 | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | 17000.01 | 2022-03-15 | 1593.75 | Spain | Madrid
A1110 | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | 17000.01 | 2022-03-22 | 6906.25 | Spain | Barcelona
A1110 | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | 17000.01 | 2022-03-29 | 5046.88 | France | Lyon
A1110 | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | 17000.01 | 2022-04-05 | 3453.13 | France | Lyon
A1120 | Slabs, beams 2 Floor | 500 | 2022-04-05 | 500 | Spain | Madrid
A1130 | Masonry Works | 2499.99 | 2022-03-22 | 833.33 | France | Lyon
A1130 | Masonry Works | 2499.99 | 2022-03-29 | 989.58 | Spain | Barcelona
A1130 | Masonry Works | 2499.99 | 2022-04-05 | 677.08 | Spain | Madrid
A1190 | Terrace Heat Insulation | 217.49 | 2022-03-29 | 190.3 | France | Lyon
A1190 | Terrace Heat Insulation | 217.49 | 2022-04-05 | 27.19 | Spain | Barcelona
A1200 | Terraces Sloped Screed | 434.96 | 2022-04-05 | 434.96 | France | Lyon
A1210 | Terraces Waterproofing | 425 | 2022-04-05 | 425 | Spain | Barcelona
A1550 | Initial Piping Works Below Ground Level | 4871.6 | 2022-02-08 | 718.76 | Spain | Barcelona
A1550 | Initial Piping Works Below Ground Level | 4871.6 | 2022-02-15 | 4152.84 | France | Lyon
A1560 | Steel Pipes & Steel Works | 10439.15 | 2022-02-08 | 782.94 | Spain | Barcelona
A1560 | Steel Pipes & Steel Works | 10439.15 | 2022-02-15 | 4523.63 | Spain | Madrid
A1560 | Steel Pipes & Steel Works | 10439.15 | 2022-02-22 | 4523.63 | France | Paris
A1560 | Steel Pipes & Steel Works | 10439.15 | 2022-03-01 | 608.95 | France | Paris